## Matrix
Updated Oct 2018
Instrument / Unit | Tier 1 subsystem (S/C view) | Tier 2 subsystem (instrument breakdown) | Make / Buy | Potential Supplier | Development Category | Design Status | Qualification Status | TRL level now | TRL end B1 | Bridge Phase prog | required deltas in B2 | TRL at end B2 added by EQM | Route to TRL6 after end B1 | Notes | Critical Item | Qty x MU (dummies) | Qty x DM | Qty x SM | Qty x ThM | Qty x STM | Qty x EFM | Qty x P-EM | Qty x D-EM | Qty x EM | Qty x EQM | Qty x QM | Qty x LTM | Qty x PFM | Qty x FM | Qty x FS | Technical Assumptions for Costing
MAG | MAG instrument boxes | MAG-OBS | Make | n/a | C - modified with delta-qual or qual | development model | Qual Not Started | 5 | 5 |  | 6 | 6 | EQM | Requires additional bridge/B2 funding | N | [6 empty] | 1 | 1 |  |  |  |  | 1 |  | 1 | Low-risk development. Fluxgate sensor elements TRL 9
|  | MAG-IBS | Make | n/a | C - modified with delta-qual or qual | development model | Qual Not Started | 5 | 5 |  | 6 | 6 | EQM |  | N | [6 empty] | 1 | 1 |  |  |  |  | 1 |  | 1 | Low-risk development. Fluxgate sensor elements TRL 9
|  | MEP Harness OB | Buy | Axon | C - modified with delta-qual or qual | design | Qual Not Started | 5 | 5 |  | 6 | 6 | EQM |  | N | [6 empty] | 1 | 1 |  |  |  |  | 1 |  | 1 | No special requirements.
|  | MEP Harness IB | Buy | Axon | C - modified with delta-qual or qual | design | Qual Not Started | 5 | 5 |  | 6 | 6 | EQM |  | N | [6 empty] | 1 | 1 |  |  |  |  | 1 |  | 1 | No special requirements.
|  | Sensor MLI OB | Buy | TBD | C - modified with delta-qual or qual | design | Qual Not Started | 5 | 5 |  | 6 | 6 | EQM |  | N | [12 empty] | 1 |  | 1 | No special requirements.
|  | Sensor MLI IB | Buy | TBD | C - modified with delta-qual or qual | design | Qual Not Started | 5 | 5 |  | 6 | 6 | EQM |  | N | [12 empty] | 1 |  | 1 | No special requirements.
|  | Electronics MAGELB | Make | n/a | C - modified with delta-qual or qual | EM (JUICE J-MAG) | Qual Not Started | 5 | 5 |  | 6 | 6 | EQM |  | N | [6 empty] | 1 | 1 |  |  |  |  | 1 |  | 1 | Low-risk development. JUICE J-MAG sub-units are at EM stage.
Instrument / Unit | Tier 1 subsystem (S/C view) | Tier 2 subsystem (instrument breakdown) | Make / Buy | Potential Supplier | Development Category | Design Status | Qualification Status | TRL level now | TRL end B1 | Bridge Phase prog | required deltas in B2 | TRL at end B2 added by EQM | Route to TRL6 after end B1 | Notes | Critical Item | Qty x MU (dummies) | Qty x DM | Qty x SM | Qty x ThM | Qty x STM | Qty x EFM | Qty x P-EM | Qty x D-EM | Qty x EM | Qty x EQM | Qty x QM | Qty x LTM | Qty x PFM | Qty x FM | Qty x FS | Technical Assumptions for Costing
PLA | PLA instrument box | PLA Optics | Make | n/a | C - modified with delta-qual or qual | EAS heritage | Qual Not Started | 3/4 | 6 | [5 empty] | Y | [6 empty] | 1 | 1 |  |  |  |  | 1 |  | 1 | development of EAS system, prototype in pre-dev programme
|  | PLA HV | Make | n/a | C - modified with delta-qual or qual | EAS heritage | Qual Not Started | 3 | 6 | [5 empty] | N | [6 empty] | 1 | 1 |  |  |  |  | 1 |  | 1 | development of EAS system, prototype in pre-dev programme
|  | PLA PSU | Make | n/a | C - modified with delta-qual or qual | EAS heritage | Qual Not Started | 5 | 5 |  |  | 6 | EQM |  | N | [6 empty] | 1 | 1 |  |  |  |  | 1 |  | 1 | low risk development
|  | PLA FBEE | Make | n/a | C - modified with delta-qual or qual | EAS heritage | Qual Not Started | 4 | 6 | [5 empty] | N | [6 empty] | 1 | 1 |  |  |  |  | 1 |  | 1 | development of EAS system, prototype in pre-dev programme
|  | FPGA Board | Make | n/a | C - modified with delta-qual or qual |  |  | 5 | 5 |  |  | 6 | EQM
|  | PLA FBEE FPGA code | Make | n/a | A - unmodified and qualified | EAS heritage | Qual Not Started | 6 | 6 | [5 empty] | Y | [6 empty] | 1 | 1 |  |  |  |  | 1 |  | 1 | changes will be minimised
|  | PLA Housing | Make | n/a | C - modified with delta-qual or qual | EAS heritage | Qual Not Started | 5 | 5 |  |  | 6 | EQM |  | N |  |  |  |  | 1 |  | 1 | 1 |  |  |  |  | 1 |  | 1 | low risk development
Instrument / Unit | Tier 1 subsystem (S/C view) | Tier 2 subsystem (instrument breakdown) | Make / Buy | Potential Supplier | Development Category | Design Status | Qualification Status | TRL level now | TRL end B1 | Bridge Phase prog | required deltas in B2 | TRL at end B2 added by EQM | Route to TRL6 after end B1 | Notes | Critical Item | Qty x MU (dummies) | Qty x DM | Qty x SM | Qty x ThM | Qty x STM | Qty x EFM | Qty x P-EM | Qty x D-EM | Qty x EM | Qty x EQM | Qty x QM | Qty x LTM | Qty x PFM | Qty x FM | Qty x FS | Technical Assumptions for Costing
MEPS | MEPS instrument box | MEPS-A | Make | n/a | C - modified with delta-qual or qual | Pre-I-PDR | Qual Not Started | 4 | 5 |  | 6 | 6 | EQM |  | Y | updated | [5 empty] | 1 | 1 |  | 1 |  |  | 1 or 2 |  | 1 | development of MEPS detector prototype in pre-dev programme
|  | MEPS-B | Make | n/a | C - modified with delta-qual or qual | Pre-I-PDR | Qual Not Started | 4 | 5 |  | 6 | 6 | EQM |  | Y | updated | [5 empty] | 1 | 1 |  | 1 |  |  | 1 or 2 |  | 1 | development of MEPS detector prototype in pre-dev programme
|  | MEPS FEEs | Make | n/a | A - unmodified and qualified | Solar Orbiter FAR | Qual Not Started | 7 | 7 | [5 empty] | Y | updated | [5 empty] | 1 | 1 |  | 1 |  |  | 1 or 2 |  | 1 | Assuming CPPA
|  | MEPS PSU | Make | n/a | A - unmodified and qualified | Solar Orbiter FAR | Qual Not Started | 7 | 7 | [5 empty] | Y | updated | [5 empty] | 1 | 1 |  | 1 |  |  | 1 or 2 |  | 1 | Assuming CPPA
|  | MEPS-BEE (include I/F FPGA design) | Make | n/a | D - new design, full qual | Pre-I-SRR | Qual Not Started | 4 | 5 |  | 6 | 6 | EQM |  | N | updated | [5 empty] | 1 | 1 |  | 1 |  |  | 1 or 2 |  | 1 | Assuming CPPA
|  | MEPS Housing | Make | n/a | D - new design, full qual | Pre-I-SRR | Qual Not Started | 4 | 5 |  |  | 6 | EQM |  | N | updated |  |  |  | 1? |  | 1 | 1 |  | 1 |  |  | 1 or 2 |  | 1
Instrument / Unit | Tier 1 subsystem (S/C view) | Tier 2 subsystem (instrument breakdown) | Make / Buy | Potential Supplier | Development Category | Design Status | Qualification Status | TRL level now | TRL end B1 | Bridge Phase prog | required deltas in B2 | TRL at end B2 added by EQM | Route to TRL6 after end B1 | Notes | Critical Item | Qty x MU (dummies) | Qty x DM | Qty x SM | Qty x ThM | Qty x STM | Qty x EFM | Qty x P-EM | Qty x D-EM | Qty x EM | Qty x EQM | Qty x QM | Qty x LTM | Qty x PFM | Qty x FM | Qty x FS | Technical Assumptions for Costing
RM | RM instrument box | RM sensors | Buy | SINTEF, St. Gobain | C - modified with delta-qual or qual | PSI heritage | Qual In Progress | 6/7-Si / 5-Sc | 6/7-Si / 5-Sc | 6/7-Si / 6-Sc |  |  | Bridge Phase | Scintillator BB in B1 (PSI funding), Heavy Ion testing in Bridge Phase | Y | [6 empty] | 1 | P-EM? |  |  |  |  | 1 |  | 1 | sensor costs as for NGRM and RADEM
|  | RM-FBEEs | Make | ENICS, microPCB etc. | C - modified with delta-qual or qual | PSI heritage | Qual In Progress | 6 / 5 | 6 / 5 | 6 |  |  | Bridge Phase |  | Y |  |  |  |  | 1 |  | 1 | P-EM? |  |  |  |  | 1 |  | 1 | similar production costs as for NGRM-BB and POLAR FEE
|  | RM-PSU | Make | ENICS, microPCB etc. | C - modified with delta-qual or qual | PSI heritage | Qual Not Started | 6 | 6 | [5 empty] | Y |  |  |  |  | 1 |  | 1 | P-EM? |  |  |  |  | 1 |  | 1 | based on production costs of POLAR CT
|  | RM-LVHV | Make | ENICS, microPCB etc. | D - new design, full qual | PSI heritage | Qual Not Started | 5 | 5 | 6 |  |  | Bridge Phase |  | Y |  |  |  |  | 1 |  | 1 | P-EM? |  |  |  |  | 1 |  | 1 | relaying on costs for adapted laboratory developments
|  | RM-Housing | Make | PSI | D - new design, full qual | Design concept | Qual Not Started | 3 | 5 |  | 6 |  | EQM | Design is being completed in B1 | N |  |  |  |  | 1 |  | 1 | P-EM? |  |  |  |  | 1 |  | 1 | low risk development
Instrument / Unit | Tier 1 subsystem (S/C view) | Tier 2 subsystem (instrument breakdown) | Make / Buy | Potential Supplier | Development Category | Design Status | Qualification Status | TRL level now | TRL end B1 | Bridge Phase prog | required deltas in B2 | TRL at end B2 added by EQM | Route to TRL6 after end B1 | Notes | Critical Item | Qty x MU (dummies) | Qty x DM | Qty x SM | Qty x ThM | Qty x STM | Qty x EFM | Qty x P-EM | Qty x D-EM | Qty x EM | Qty x EQM | Qty x QM | Qty x LTM | Qty x PFM | Qty x FM | Qty x FS | Technical Assumptions for Costing
XFM | XFM instrument box | XFM Sensors | Buy | Oxford Instruments Technologies | C - modified with delta-qual or qual | Designed | Qual Not Started | 4 | 4 | 6 |  |  | Bridge Phase | [8 empty] | 1 | 1 |  |  |  |  | 1 |  | ?
|  | XFM FEEs | Buy | ASRO | C - modified with delta-qual or qual | Designed | Qual Completed | 4 | 4 | 6 |  |  | Bridge Phase | [8 empty] | 1 | 1 |  |  |  |  | 1 |  | ?
|  | XFM PSU | Buy | ASRO | D - new design, full qual | Partially New | Qual Not Started | 4 | 5 |  |  | 6 | EQM | 5 justified as standard parts amd techniques | [7 empty] | 1 | 1 |  |  |  |  | 1 |  | ?
|  | XFM-BEE(including interface FPGA design) | Buy | ASRO | C - modified with delta-qual or qual | Designed, Needs updates (nr of detectors, SpW I/F) | Qual Not Started | 4 | 5 |  |  | 6 | EQM | 5 justified as standard parts amd techniques | [7 empty] | 1 | 1 |  |  |  |  | 1 |  | ?
|  | XFM housing | Buy | Talvioja | C - modified with delta-qual or qual | Needs modification | Qual Not Started | 3 | 5 |  |  | 6 | EQM | [6 empty] | 1 |  | 1 | 1 |  |  |  |  | 1 |  | ?
Instrument / Unit | Tier 1 subsystem (S/C view) | Tier 2 subsystem (instrument breakdown) | Make / Buy | Potential Supplier | Development Category | Design Status | Qualification Status | TRL level now | TRL end B1 | Bridge Phase prog | required deltas in B2 | TRL at end B2 added by EQM | Route to TRL6 after end B1 | Notes | Critical Item | Qty x MU (dummies) | Qty x DM | Qty x SM | Qty x ThM | Qty x STM | Qty x EFM | Qty x P-EM | Qty x D-EM | Qty x EM | Qty x EQM | Qty x QM | Qty x LTM | Qty x PFM | Qty x FM | Qty x FS | Technical Assumptions for Costing
DPU | DPU instrument box | DPU CPU Unit | make | IAP | D - new design, full qual | Design concept | Qual Not Started | 4 | 5 |  | 6 |  | EQM |  | N | [6 empty] | 1? |  | 2 |  |  |  | 2 |  | 1 | To reduce cost, a single FS board shall be built (as repair kit)
|  | DPU Software Image | TBD | IAP/Czech industry | D - new design, full qual | Design concept | Qual Not Started | 5 | 6 | [5 empty] | Y | [6 empty] | 1? |  | 1 |  |  |  | 1 |  | 0 | TRL definition for software is unclear
|  | DPU PSU | make | IAP | D - new design, full qual | Design concept | Qual Not Started | 4 | 5 |  | 6 |  | EQM | 5 justified as standard parts amd techniques | N | [6 empty] | 1? |  | 2 |  |  |  | 2 |  | 1 | To reduce cost, a single FS board shall be built (as repair kit)
|  | DPU Power Management Unit | make | IAP | D - new design, full qual | Design concept | Qual Not Started | 4 | 5 |  | 6 |  | EQM | 5 justified as standard parts amd techniques | N | [6 empty] | 1? |  | 1 |  |  |  | 1 |  | 1
|  | DPU SpW Mux Board | make | IAP | D - new design, full qual | Design concept | Qual Not Started | 4 | 5 |  | 6 |  | EQM | 5 justified as standard parts amd techniques | N | [6 empty] | 1? |  | 1 |  |  |  | 1 |  | 1
|  | DPU Housing | TBD | IAP/Czech industry | D - new design, full qual | Design concept | Qual Not Started | 4 | 5 |  |  | 6 | EQM |  | N | [6 empty] | 1? |  | 1 |  |  |  | 1 |  | 1
DPU Instrument

## TRL definition
ECSS ECSS-E-HB-11A TRL definition
Click on page image to open file

## Drop-Downs
Qualification Status | Development Category | Make / Buy
Qual Not Started | A - unmodified and qualified | Make | Y
Qual In Progress | B - unmodified with delta-qual | Buy | N
Qual Failed | C - modified with delta-qual or qual | TBD
Qual Completed | D - new design, full qual