## PMI (hidden)
Document | Section | Reviewer | Comment
LGRRS-MPS-ICD-100001_D_a=PMI_Instrument_to_SC_ICD (v2) | 4.2.2. | BO | 60 arcsec are very challenging. Definintions of co-alignment and the contributing factors will be included in the spacecraft to instrument ICD.
| 4.2.3. | CB | The RPE requirements do not specify a timescale over which RPE is computed, so strictly speaking they are not RPE requirements. It is important to specify a timescale for the RPE computation. The requirements does not specify which axes the requirement applies to; please update to specify the axes. It is noted that the requirements differ from both Solar Orbiter LOS and ALOS requirements; a proper comparison will be performed when the applicable axes are specified.
| 4.3.1. | BO | Does this refer to lateral alignment or radial alignment (shimming)? Shall we start to correct after +- 1mm, or allow correction up to +-1mm? Corrections of +- 1 mm seem to be a lot (typical values for lateral alignment are 0.1 mm, shimming 5 *10^-6 m). Please provide reasoning to allow better understanding of this requirement.
| 4.3.5. | CB | The allocated volume is far larger than the IRD which is 200 x 200 x 800. Is the allocated volume correct, and if so what is the reason for such a large increase? Is there any reduction expected in this volume in the future?
| 4.3.7. | BO | Could you please provide details on the opening mechanism: - Is the mechanism powered by a motor or a spring? - Are there pyrotechnics in the mechanism for the door hold down? This information is needed to understand what impact the mechanism could have on the platform.
| 4.3.7. | CB | When does the door need to be shut during the mission? This needs to be understood for planning the mission CONOPS. The multi-use mechanism is now TBD. If a multi-use mechanism is not implemented then the door could not be closed if nominal Sun pointing attitude is lost, and could not be closed during delta-V manoeuvres (off pointing from the Sun). Is this acceptable?
| 4.3.7. | CB | Which way does the door open? Is there any flexibility in specifying this from a spacecraft accommodation perspective? This is asked to understand options in spacecraft accommodation.
| 4.4 | AJ | The approach for the thermal control of the PMI Optics Unit is not understood. PMI-ICD-4101 specifies that the Optics Unit is thermally insulated from the spacecraft (so decoupled from the interface), when PMI-ICD-4401 & 4402 indicate that the interfaces shall be thermally controlled, which then seems contradictory and unneeded. Please clarify.
| 4.4.1 | AJ | PMI-ICD-4101: having the Unit decoupled from the spacecraft means that the PMI payload is provided with its own thermal control sub-system (except for survival heaters), independent from the platform TCS. Please confirm.
| 4.4.2. | BO | What are the heat fluxes of the interfaces? PMI-ICD-4202: Why is the minimum non-operational temperature (-30 degC) higher than the minimum operational temperature (-40 degC)? PMI-ICD-4205: The small temperature range of 15°C is challenging (considering margins and uncertainty), is this really required? PMI-ICD-4207: Why does the electronic unit have such a small temperature range? -20 to +40 would be expected PMI-ICD-4209: This may be challenging, is this needed only when the instrument is operational or also when it is non-operational?
| 4.4.4 | CB | PMI-ICD-4401 and PMI-ICD-4402: More definition of these interfaces are required. What is the heatflux from the interfaces, what mechanical loads can the interfaces withstand, what is the geometry of the cold interfaces to the PMI mounting interfaces?
| 4.5.1 | AJ | The average power is needed for each of the units (Optics and EU).
| 4.5.1. | BO | The instrument (instrument package) is expected to be compatible with an unregulated bus voltage (26 - 34 V). This will be formulated in the spacecraft to instruments ICD. Peak power is specified; please also provide the average power consumption. In the future a more detailed power budget for each instrument mode will be required.
| 4.6.2. | BO | Could you please provide background information to this requirement- what is the reason behind? Are these telecommands to be expected from IPCU or from S/C?
PMI-ICD-6301 and PMI-ICD-6302: these requirements should be applicable to the IPCU not the S/C. The IPCU shall then have a requirement stating what data rate the S/C shall cope with.
| 4.6.3 | CB | PMI-ICD-6303 The table shows three options for cadence, however for on-board processed data modes the cadence of 60s corresponds to 1608 kbps. This is significantly more than the goal data rate in PMI-ICD-6301 which is 982.9 kbps. Does a cadenced of 60s need to be considered? For the raw data modes all cadences correspond to data rates higher than is currently designed for in the RF downlink. The raw data will therefore need to be stored in mass memory and downlinked at the speed of the RF downlink. Is it expected for the IPCU to have the mass memory for storing this raw data, or does the platform need to have the mass memory?
| 4.6.3. | BO | 6303: To size the memory on the S/C, please indicate the frequency and duration of the raw data mode.
| 4.6.4. | RL | The S/C shall provide an absolute onboard time to PMI which can be correlated to UTC to an accuracy of 5ms (tbc). Needs to be analyzed since referenced to UTC. On-board certainly ok with SpW.
| General | ML | How often is calibration required during the mission and how long will it take? Is any decontamination required for PMI. If yes, when, how often, which duration? This is important to plan the mission CONOPS
| General | CB | A distinction needs to be made for requirements which are applicable to the S/C and requirements which are applicable to the IPCU. Sections 4.6.2, 4.6.3 and 4.6.4 are all applicable to the IPCU and not the spacecraft.
| General | BO | Does PMI have a sensor to check the status of the multiple shut door? Please include the presence and purpose (measurement) of sensors in the instrument ICD. This is important for the FDIR concept.
| General | RL | PMI does not show dedicated dedicated heater lines, are they covered by power interface?

## COR (hidden)
Document | Section | Reviewer | Comment
LGRRS-RAL-ICD-3001v0.24_COR_Instrument_to_SC_ICD.pdf | 4.2. | BO | Is the location of the side facing radiator fixed, or can the detector radiator be mounted on the other side of the instrument? Fig. 5-17 suggests that the radiator position can change. This is asked to understand accommodation options for the instrument.
| 4.2. | RL | Fig. 4.3. shows survivial heater thermostats and survival temperature sensors. Why are temperature sensors needed for thermostats?
| 4.3 | BO | Is there a time limit for how long the shutter or door can be exposed to the Sun?
| 4.4. |  | CME detection – potentially used as a trigger for higher cadence acquisition: is it expected to switch to a different mode in case of a solar event? This is not in line with the information provided to system study at PM1.
| 5.2.2. | BO | Please provide AD3 (or include the co-alignment requirements here)
| 5.2.3. | BO | Definitions of pointing errors (APE, RPE, PDE) shall be in accordance with the ESA handbook (ESSB-HB-E-003). It is proposed to add this document as RD1. The RPE requirements do not specify a timescale over which RPE is computed, so strictly speaking they are not RPE requirements. It is important to specify a timescale for the RPE computation.
| 5.2.3. | BO | PRE is defined over 'several days'; a definitive number of days needs to be stated in the requirement. On SolO, the achieved performance for the AOCS alone is of the order of 15” to 25”. Furthermore, the thermos-elastic deformation between STR and instruments needs to be taken into account. On SolO, this contribution is between 23" to 45" depending on instrument. Although L5 provides a more stable temperature environment, PRE of 10 arcsec over several days will be highly challenging for the spacecraft. Could you please provide clarification on the reason for such tight requirement?
| 5.2.4. | BO | Field of regard: is it allowed to have other instrument apertures in the plane of the COR aperture? (or out of which radius?) Does COR need "to stick out" of plane with other apertures?
| 5.3.1. | BO | Is the CEB also designed for being mounted outside of S/C or shall it be mounted inside?
| 5.3.2. | BO | COR mass according to Inst. Budget =11.5 kg, which is very different to the 20 kg required in R-IRD-COR-INS-0010. Please indicate which one is applicable.
| 5.3.2. | CB | Base plate, supports and Top plate, mounting posts are removed from new mass budget in the Inst. Package Budget report. Are they included in other budget, or will they not be there?
| 5.3.5. | BO | The unit dimsions vary: Section 4.3 and 5.3.5. and Fig.5-15: 340x340x880 mm^3, Req. COR-ICD-0765: 800x340x340 mm^3. Please clarify which one is correct.
| 5.3.7. | BO | Please include also information on shutter here: - Is the shutter ever used during nominal operations (e.g. for calibration)? - The text says that neither mechanism will operate during normal operations, yet Sec. 4.3. states that the shutter may be closed to protect during thruster firing. Note that in nominal operations, the thruster will be fired approximately once every two weeks
| 5.3.7. | CB | Is there any flexibility in which way the door opens or is the opening direction definitely fixed? This is asked to understand options in spacecraft accommodation.
| 5.4.2. | BO | Decontamination heaters: how often and for how long are they needed? In initialisation phase and also during routine phase?
| 5.4.2. | BO | Survival heaters: From S/C point of view, the preference would be thermistors but thermostats are acceptable to maintain the current design.
| 5.4.2. | AJ | "Survival heaters will be supplied by the sc survival power supply and controlled with thermostats", this is in contradiction with the IPCU ICD that specifies IPCU-ICDRS-4101 (§4.4.2) that the survival heaters are to be powered and controlled directly by the S/C by means of thermistor triplets.
| 5.4.2 | CB | COR-ICD-0860: says S/C shall not be responsible for COR thermal control but survival heaters / thermostats are under S/C responsibility?
| 5.4.2. | BO | Please provide temperature limits in the same format as PMI ICD (maximum and minimum operational and non-operational temperatures for each unit).
| 5.4.3. | AJ | Is there a reason for using Black Kapton MLI (high absorption of solar flux) when the payload needs to be maintained at cold temperature? Is it for EMC concerns?
| 5.4.3. | BO | Please include the redundant power line.
| 5.6.5. | BO | How many power interfaces are expected from S/C side? Is it 1 N + 1 R as shown in Fig4-3, or is it 2x(1 N+1 R) for CEB and COR?
| General | RL | The COR ICD requirements describe only the electrical interface to the S/C but not the interfaces to the IPCU. This is different to other instruments. It is recommended keep the information in one document at the present stage to allow better understanding, and to clearly identify which requirement applies to IPCU and which to S/C.

## HI (hidden)
Document | Section | Reviewer | Comment
LGRRS-RAL-ICD-4001v0.2_Helios-Imager_Instrument_to_SC | 4.2. | CB | From S/C point of view, the preference would be thermistors but thermostats are acceptable to maintain the current design.
| 4.2., 5.3.7. | RL | Fig. 4.1. shows the door opening power line towards the IPCU, while it should be directly to the S/C (as also stated in Section 5.3.7.). The microswitches could be either to IPCU or S/C.
| 4.3. | BO | Please can the ICD include a diagram for the fields of view.
| 4.3. | BO | Are there any extra radiators needed beyond the one on the HI structure? (on S/C side)
| 5.4.2. | BO | Decontamination heaters: how often and for how long are they needed? Only in initialisation, or also during routine phase?
| 4.3 | CB | Having a shutter is very useful as it simplifies the AOCS and FDIR designs. It is strongly recommended to keep the shutter in the design.
| 4.2. | BO | Fig 4-1: How many power interfaces are expected from S/C side? Is it 1 N + 1 R or is it 2x(1 N+1 R) for HI-1 and HI-2?
| 5.2.2. | BO | Please povide AD3 or include the inter-instrument co-alignment requirements also here.
| 5.2.3. | BO | Definitions of pointing errors (APE, RPE, PDE) shall be in accordance with the ESA handbook (ESSB-HB-E-003). It is proposed to add this document as RD1.
| 5.2.3. | BO | A PDE of 30 arcsec over several days will be challenging for spacecraft. Solar Orbiter has a PDE around 50". Please provide clarification on why such a tight requirement is needed. 'Several days' for PDE requirement needs to be changed to a definitive number of days. The RPE requirements do not specify a timescale over which RPE is computed, so strictly speaking they are not RPE requirements. It is important to specify a timescale for the RPE computation.
| 5.3.2. | CB | R-IRD-HI-INS-0010 indicates as mass of less than 20 kg, while the mass budget report gives 23.4 kg. Which mass shall be taken into account?
| 5.3.3. |  | The unit dimensions with door opened changed from ICD v1 840 mm (length) x 1100 mm (width) x 240 mm (height) to ICD v2 840 mm (length) x 1100 mm (width) x 260 mm (height). This is the same hight as for HI with closed door. Is this correct, and where does the change come from?
| 5.3.7. |  | "One of the direct electrical interfaces between the HI and the spacecraft is switched power (nominally 28 V) from the spacecraft pyro bus to operate the wax actuator and release the HI door; two redundant circuits are provided." Please indicate the total number of electrical interfaces towards the S/C. Fig. 4-1 does not show an electrical interface bewteen S/C and HI except for the survival heaters.
| 5.3.7. | BO | Could you please provide details on the door and shutter opening/closing mechanism: - Is the mechanism powered by a motor or a spring? - Are there pyrotechnics in the mechanism for the door hold down? This information is needed to understand what impact the mechanism could have on the platform.
| 5.4.1. | BO | Temperature range of +10 to +30 °C for spacecraft I/F temperaure is very small, is it possible to increase this range? Is this temperature required during operating and non-operating periods of HI?
| 5.4.2. | AJ | "Survival heaters will be supplied by the sc survival power supply and controlled with thermostats", this is in contradiction with the IPCU ICD that specifies IPCU-ICDRS-4101 (§4.4.2) that the survival heaters are to be powered and controlled directly by the S/C by means of thermistor triplets.
| 5.4.2. | BO | 4 survival heaters are foreseen (1 N+1 R for HI-1 plus 1 N +1R for HI-2); yet Fig.4-1 shows only 1N+1R power line from S/C to survival heaters; is this correct?
| 5.4.3. | BO | Please include number of power lines (N+R) for survival heater power directly to HI
| 4.3. | BO | Is there a time limit for how long the shutter or door can be expose to the Sun?
| 5.6.6. |  | "It is assumed that the FEEs are supplied with nominal and redundant primary power supplies. It is assumed that HI is supplied with nominal and redundant survival power supplies" Please specify the number of power supplies you need from the IPCU and from the S/C.
| general |  | To facilitate review, it would be appreciated if section numbering remains rather stable.
| additional |  | Does HI have sensors to check the status of the shutters? Please include the presence and purpose (measurement) of sensors in the instrument ICD. This is important for the FDIR concept.
| additional | CB | A precise definition of the straylight constraints needs to be provided in the document. This would be most usefully defined as a plane which is a certain distance from the mounting interface above which no item should protrude
LGRRS-RAL-RP-0001v0.4 Budget report | 2. and 2.2. | CB | In Section 2.2., the power budget for HI shows 28 W peak including 20 % margin. This is not in line with the information provided in Section 2.2.: 34.6 peak power.
version 1 | v1, 4.4 | BO | What UFOV is required for the radiators?
version 1 | v1, 4.7.3. | BO | The final integration is usually in clean room of class 10 000 or 100 000. In case a end-to-end test including the door opening is foreseen in class 1000, this may become a cost driver.

## EUVI (hidden)
Document | Section | Reviewer | Comment
LGRRS-CSL-ICD-2001v0.3_DRAFT_EUVI_Instrument_to_SC_ICD.pdf | 3.1. | BO | EUVI-ICD-7102: what is the best estimate for the duration of decontamination and how often decontamination is required?
| 3.3. | BO | EUVI-ICD-2102: Are there special requirements on the mounting of the electronic box? (Close / below optic unit). From Fig. 3 in section 3.3, we assume it will be mounted also outside of the S/C.
| 4.2.1. | BO | EUVI-ICD-2104: the COR and HI will be partially in the view of the radiator. What UFOV is required for the radiator? It is assumed that the instrument contractor will be responsible for sizing the radiator.
| 4.2.1. | BO | Please specify the required size of the unobstructed field of fiew
| 4.2.2. | BO | Co-alignment with all remote sensing instruments required? The HI FOV does not overlap with the EUVI FOV. Definintions of co-alignment and the contributing factors will be included in the spacecraft to instrument ICD.
| 4.2.3. | CB | The requirement does not specify which axes the requirement applies to; please update to specify the axes. It is understood that the main heritage for EUVI is EUI from Solar Orbiter. EUI on Solar Orbiter has RPE specified over a different timescale and with a different threshold: - RPE <1 arcsec over 10s, half cone at 95% level for LOS - RPE <2 arcsec over 10s, half cone at 95% level for ALOS What is the reason for the tighter pointing requirement on Lagrange Mission?
| 4.2.4. | BO | What is the line-of sight? What is the required unobstructed field of view?
| 4.2.4. | CB | Required field of view is not clear. Two angles are specified: 61.3’x42.6’; it is assumed one of these is the angle in the ecliptic plane and one is the angle out of the ecliptic plane, however it is not clear which one is which.
| 4.3.2. | CB | EUVI-ICD-3202: the term "mass tolerance" should be replaced with "mass margin". Mass allocation will be basic mass plus margin= 12.6. kg?
| 4.3.5. | BO | We assume this volume includes optical and electronic box
| 4.3.5. | CB | What is meant by tolerance? Does this mean the dimensions could be 20% larger than those specified? Maximum dimensions are requested.
| 4.3.7. | BO | Could you please provide details on the opening mechanism: - Is the mechanism powered by a motor or a spring? - Are there pyrotechnics in the mechanism for the door hold down? This information is needed to understand what impact the mechanism could have on the platform.
| 4.3.7 | CB | From the images it looks like the doors only open by 90°. This will mean the EUVI needs to be mounted lower than the COR to ensure the EUVI doors do not enter the COR unobstructed field of view. If the doors only open by 90° it is assumed the unobstructed field of view for EUVI will be quite narrow?
| 4.3.7 | CB | Which way do the doors open? Is there any flexibility in specifying this from a spacecraft accommodation perspective? This is asked to understand options in spacecraft accommodation.
| 4.4. | BO | Please provide temperature limits in the same format as PMI ICD (maximum and minimum operational and non-operational temperatures for each unit).
| 4.7.1 |  | For how long does EUVI needs to be open without UV light entering in optical path? What is required pointing angle?
| 4.4.2 |  | When/how often and how long is decontamination required in flight?
| 4.7.1 | BO | Please provide details of what is required for calibration? - Does the spacecraft need to be slewed away from the Sun and by how much? It is understood that if a multiple opening/closing door is used then off pointing from the Sun would not be required. This would be preferred at System level. - How often does calibration need to be performed, and for how long?
| 4.7.3. | BO | The cleanliness level of internal surfaces can not be under responsibility of the S/C integrator (potential contamination before delivery to integrator). No cleanliness requirement is specified for external surfaces; if 50 ng/cm2 molecular cleanliness and 54 ppm particulate cleanliness is required this is highly challenging and will become a cost driver. The S/C integrator will provide purge flow; spacecraft to instruments ICD will specify the gas and gas cleanliness to be used for purging as well as the maximum purge outage and recovery duration.
| 5.1. | RL | EUVI-ICD-5102: Is the EUVI compatible to 28V unregulated? What means no regulation?
| 6.4. | RL | EUVI-ICD-6401: The S/C shall provide an absolute onboard time to EUVI which can be correlated to UTC to an accuracy of 5 ms (TBC). Needs to be analyzed since referenced to UTC. On-board certainly ok with SpW.
| 6.4. | RL | EUVI-ICD-6402: The S/C shall provide synchronism between EUVI and PMI observations (cadence) of better than 100ms within 1 hour (TBC). Needs inter-instrument coordination -> Chapter 4.6.5.
| General | RL | EUVI does not show dedicated heater lines, are these covered by power interface?
| additional | BO | Does EUVI have sensors to check the status of the multiple shut doors? Please include the presence and purpose (measurement) of sensors in the instrument ICD. This is important for the FDIR concept.

## IPCU (hidden)
Document | Section | Reviewer | Comment
LGRRS-ADS-ICD-5001v0.2_IPCU_to_SC_ICD_20170502_final.pdf | 3.2 | RL | The picture of the electrical functionality shows direct SpW interfaces to the GPM for PMI and COR. Why are the HI and EUVI SpW lines routes through the CIM module, what is the specific processing needing this routing?
| 4.5.6 | RL | Grounding diagram refers to GPM module but it is actually the complete IPCU with all interfaces. There is no Milbus; SHP, RSA and operational heaters are missing. Minor, could be amended for next issue.
| 4.5.2. | BO | What is total amount of power lines from S/C to IPCU?
| General | BO | Please include the expected data rates from IPCU to SC.
| General | CB | The individual instruments ICDs and DPU ICD do not provide any information about FDIR design. Do the instruments and/or IPCU have the capability to monitor and detect failures? What action is taken in the event of a failure occuring?

## General RS (hidden)
Applicable | Comment
PMI, COR, HI, EUVI | It needs to be clearly stated what is a requirement towards the S/C, and what is a requirement towards the IPCU.
All Instruments and IPCU | The instruments are expected to be compatible with an unregulated bus voltage (26 - 34 V)provided by the spacecraft. This will be formulated in the spacecraft to instruments ICD.
All Instruments and IPCU | It is understood that harness between instruments and IPCU is not included in this mass budget. This harness should therefore be included in the instrument mass budgets. Harness between IPCU and platform will be included in the platform mass budget. ( The length of the harness will depend on the placement of the IPCU in the spacecraft and the requried routing. The spacecraft will provide the length of the required harness.)
All Instruments and IPCU | The total power consumption for the remote sensing instrument package is 160 W (vs 100 W as specified in the SRD).
All instruments | Please include the expected instrument modes in the ICDs.
All instruments | In case instrument has sensors to monitor the shutter or door position, please include in the ICD.
All instruments | Please indicate how often and for which duration each instrument needs to be in raw data mode. This is important to size the S/C memory.
All instruments | Mass budget is not shown in the ICD (COR; HI, PMI) and is now in AD4, however EUVI ICD shows mass budget in its ICD. A consistent approach should be followed across all instruments.
All instruments | When/how often and how long is decontamination required in flight (initialisation, routine phase)?
All instruments | Heater lines for instruments seem not be addressed in instrument ICDs but are shown in the IPCU ICD.
All Instruments and IPCU | In case no switching capability if foreseen in the IPCU for instrument power lines, instruments above e.g. 20W should be able to be switched off. This could be in PCDU (SO-LCL) or in the instruments, if no power distribution is done in IPCU. See also general comment above on power distribution concepts. (The power distribution concepts for 28V between remote and in-situ should be aligned. In-situ provides in the DPU the switching capability of power lines, potentially further capabilities as power conditioning etc. . The IPCU relies on the S/C. Both concepts are considered feasible.)

## MAG
Document | Section | Reviewer | Comment
LGR-MAG-ICD-Issue_A.pdf | 5.1.1. | BO | Fig 5.2 is difficult to read, a better resolution would be appreciated
| 5.2.1. | BO | "one face shall be permanently iluminated by the sun": does that refer to a specific side of the sensor, or is the requirement that ilumination shall be constant?
| 5.2.2. | BO | Is it correct that OB-X shall be aligned with IB-Y? Does that mean OB-Y shall be aligned with (-) IB-X, and OB-Z to IB-Z?
| 5.2.2. | BO | The accuracy of the alignment measurement is likely to be similar to that achieved on Solar Orbiter and JUICE.
| 5.6.1. | BO | There seems to be an inconsistency in the 20 bit resolution vs 16 bit resolution given in Section 4.2.
| 5.9.2.3. |  | What is driving the 5 nT requirement? This is a more stringent requirement than Solar Orbiter which was 20 nT. It is understood that more post-processing may be required if there is a larger magnetic field at the OBS, but for an L5 mission this should be acceptable. 5 nT are very challenging and will lead to an increased boom size. We would like to suggest to relief the requirement to 20 nT as threshold, and 10 nT as a goal.
| general | BO | We understand that there are no survival heaters, and no direct electrical interfaces with the spacecraft
|  | CB | Is there strain relief for the harness at exit points from the OBS and IBS?
| 5.3.2. | CB | The mass budget table should show the mass without margin and the mass with margin. A total mass should be provided for all units.
| 5.5.1. | CB | The power budget table should show the power without margin and the power with margin. A total power should be provided for all units.
| 5.8.1. | CB | What in flight calibration is needed, how often does it need to be performed and what is the duration?
| 5.8.1. | CB | An 'off mode' should also be included in the list.
| 5.8.1. | CB | Please provide a mode transition diagram.
LAGRANGE MAG EMC CONSIDERATIONS | 5.1.1. | BO | 5 nT is very challenging, see comment on 5.9.2.3. Please specify the contributions to "remanent", "induced" and "stray" in order to avoid misunderstanding. We assume "stray" refers to contributions from currents, and "induced" coming from the environment at L5.
| 5.1.2. | MP | Is a boom-deployed fall-off test on the ground necessary? This may be done as part of in-flight commissioning so long as the MAG sensor is turned on before deployment.
| 5.2.2. | SK, MP | "The peak-to-peak time variation of the system magnetic field magnitude (i.e. remanent plus stray plus induced) at the position of the MAG outboard sensor shall be less than 0.5 nT in the frequency band between 0.0001 Hz to 1 Hz." Does this apply to routine phase only, or also to transfer phase or other phases? Periodic operation of mechanical-switching components should be excluded as thruster operation and firing, for example, is likely to exceed a change in 0.5nT.
| general | SK | There are no requirements on time stamping load change events and non-periodic events. Please include the requirement if needed.

## PLA
Document | Section | Reviewer | Comment
MSSL-LGR-ICD-18003_ICD_PLA_ISSUE_A.pdf | 5.2.4. | BO | What is the line-of-sight of the PLA instrument? (see sketch). Is our assumption correct, that the line of sight lies in the ecliptic? What is the difference between 'intrinsic FOV' and 'observational FOV'? What is meant by unobstructed FOV azimuthal being '+22.5° - 22.5°' whereas it is '-22.5° - +22.5°' for the intrinsic and observational FOVs? A diagram shall be included in the next version of the ICD to clearly define the line of sight and field of views for the PLA.
| 5.2.4. | BO | Is direct sunlight allowed to fall into the sensor? If yes, is there a limit in the duration for which PLA can sustain direct sunlight inside its detector?
| 5.4.1. | BO | Why is the minimum non-operational temperature (-5 degC) higher than the minimum operational temperature (-10 degC)?
| 5.5.3. | BO | Table 5-9, see also Figure 5-4 Besides HV disable/airsafe plug, no electrical interfaces directly with S/C, is that correct?
| 5.7.3. |  | The S/C integrator will provide purge flow with Gaseous Nitrogen GN2 class 5 TBC; spacecraft to instruments ICD will specify the gas and gas cleanliness to be used for purging as well as the maximum purge outage duration.
| 5.7.3. |  | The cleanliness level of internal surfaces (MCP, Analyser Aperture) can not be under responsibility of the S/C integrator (potential contamination before delivery to integrator). How is it expected to proove that external surfaces fulfill the contamination requirement at delivery?
| general |  | Are there any temperature sensors envisaged in the design? In case yes, please include the presence and purpose (measurement) of temperature sensors (for survival or other heaters) in the instrument ICD. This is important for the FDIR concept
| 5.2.3 | CB | "PLA shall have absolute pointing knowledge that is better than ±0.25°" This is understood to be an AKE requirement. Definitions of pointing errors and requriements formulation shall be in accordance with the ESA handbook (ESSB-HB-E-003). This should be added as a reference document. "PLA instrument to spacecraft alignment shall be better than ±0.5°" - it is assumed this is referring to alignment with the spacecraft reference.
| 5.3.5 | CB | Figure 5-3: width between mounting feet (113 mm) is provided, but maximum width of the unit is not provided. Please update to provide this. Are the envelope dimensions the maximum possible dimensions including tolerances? If not then they should be updated to be maximum dimensions, or the tolerances should be specified.
| 5.4.2 | AJ | It is understood that the PID controlled heaters (non-magnetic resistors) are the responsibility of the payload (sizing, procurement, installation). Please confirm.
| 5.4.3 | AJ | Will this heatshield be provided by payload?
| 5.4.4 | AJ | The thermal HW interface info is missing (coupled or decoupled from the sc). This info is required as it defines the whole thermal control approach for the instrument. If MLI is required on PLA it shall be designed and provided by the instrument supplier.
| 5.4 | CB | No information is provided for survival heaters; this section should be updated to provide details. It is assumed that survival heaters and survival temperature sensors are selected based on analysis by the instrument team, and procured and fitted by the instrument team. These will then be controlled by the spacecraft. The instrument should use thermistors as survival temperature sensors and not thermostats.
| 5.6.1 | CB | Eng. Mode 1 – MCP health check and Eng. Mode 2 – MCP pulse height distributions Do these need to be considered as an unavailabilities of the instrument of 2 x 1 minute per week? Eng. Mode 3 – STIMs for threshold checking Does this need to be considered as an unavailabity of the instrument of 1 minutes every 6 months? Eng. Mode 5 – HV checkout mode and Eng. Mode 6 – FPGA self-test mode Do these need to be considered as an unavailabity of the instrument of TBD minutes every 6 months?
| 5.6.1 | SI | Which required DPU capabilites are referred to for recieving the listed additional data products ?

## MEPS
Document | Section | Reviewer | Comment | Answer
MSSL-LGR-ICD-18004_ICD_MEPS_issue_B | 4.1. | BO | What is resulting magnetic moment of magnets? This is asked to ensure the magnetic field of the instruments will not affect the MAG measurements | The compensated magnet system which will be used in MEPS is inherited from the compensated magnet system which is used in Solar Orbiter EPT-HET1&2 and STEP. All these units passed the stringent DC Magnetic field requirements as well as extensive H-field characterization. The following magnetic requirements are examples from Solar Orbiter project which Kiel units are compliant with them: Maximum permitted magnetic dipole = 10 mAm^2 Maximum permitted dynamic DC magnetic field measured at 1m = 18 nT Maximum permitted periodic transient measured at 1m = 110 pT
| 4.1. | BO | What calibration activities have to be performed in flight, how long will they last and how often do they need to be performed? What information is needed from other electron / ion instruments, and with which frequency? If one MEPS unit is being calibrated (or other downtime) and the other is still operational, is the MEPS instrument still considered available or do both units need to be operational for the instrument to be considered operational? This is needed for the System availability budget. | MEPS transmits a small fraction of its data as full-resolution data which serve for all in-flight calibration activities of MEPS. Should we require more such data, this would not interrupt MEPS operations, but could be achieved by increasing the telemetry budget of MEPS for a limited amount of time (typically a few days).
| 5.2.3. | BO | How strict is UFOV requirement? To be discussed | It is strict especialy for the proton-ion telescope. The electron telescope could tolerate a blockage up to 10%). To be assessed case by case.
| 5.2.3. | BO | Straylight: discussion or better specification needed (how much straylight corresponds to 0.1 nA leakage current?) | 3W/m^2 according to the latest straylight assessment for Solar Orbiter. In past missions we received the S/C light distribution on a screen in front of the instrument apperture and a ray tracing method was then applied.
| 5.4.1. | BO | Please include the presence and purpose (measurement) of temperature sensors (for survival heaters) in the instrument ICD. This is important for the FDIR concept | Already included in section 5.4 issue D. "(c): MEPS uses S/C controlled survival heaters: MEPS will require a separate control line (harness) in order to control the temperature of the unit based on the unit survival compartment temperature sensors output and the unit survival heaters. These are designed as part of the unit thermal control subsystem and will be monitored and controlled by the S/C thermal control system."
| 5.4.1. 5.4.3. | BO | We understand that there shall be one nominal power line and analogue signal (TBC) between S/C and MEPS sensor to supply the survival heaters. Is there also a redundant line foreseen? How many survival heaters are planned? How many temperature sensors are planned on the survival heaters? This is important for the FDIR concept Regarding the type of temperature sensors: From S/C point of view, the preference would be thermistors (which have a better tolerances on the set-points, are more flexible (set-points can be adjusted during testing or during the mission), allow a thinner switch-band (so lower heater power consumption expected) and are cleaner w.r.t. EMC concerns) | In Solar Orbiter there are three "survival" thermistors to apply "majority voting method" and two standard RICA foil survival heaters (one nominal and one redundant). The thermistors are: Part number: G15K4D489, NTC thermistor 15kOhm, operating range -60°C to + 160°C
| 5.4.1. | BO | How strict is requirement on solar ilumiation when operating? To be discussed | o The direct solar illumination on the instrument will have thermal impact. However these impacts can be minimized by the selection of the appropriated unit thermal hardware (MLI, radiators, etc). o The direct solar illumination on the instrument will also have a performance impact o If the instrument collimator and/or detector receive solar illumination, the leakage current induced in the detector will increase and the signals will become noisy and unusable. o Thus, the unit collimators cannot receive direct illumination during nominal operation. The unit can be switched off during manoeuvres. o A sun shield is required. the ICD and TN4 show the instalation of a local sunshield protecting one of the MEPS locations in front of the S/C
| 5.4.1 | CB | In case of failure, what is the duration of acceptable solar ilumiation on the instrument / on the telescopes? It is assumed that the requirement not to receive direct solar illumination is only applicable when MEPS is operating. If this is also applicable when MEPS is not operating then this will have to be considered for initial sun acquisition and also safe mode, and could become a driver for the AOCS/FDIR design. | From the performance point of view (see above): MEPS cannot be operated when the collimators are iluminated. The unit needs to be switched off in these cases. In operational case the collimators need to be protected by means of a sunshield.
| 5.5.1. | BO | Is the power budget given in table 5-4 for one MEPS unit or for two MEPS units? (We understand that sensor MEPS-A and sensor MEPS B form together one unit) In case two units are used as suggested in Section 5.2.2., does that mean the power budget increases to 2 x 4.7 W (+2x2W for operational heaters) | 5-4 is the power budget for ONE MEPS unit. One MEPS unit consists of two sensors A and B. Right, two MEPS units will double both power budgets (instrument and operational heaters)
| 5.3 | CB | This ICD should cover the whole instrument, i.e. 2 units. The mass budget should therefore clearly show the total mass for 2 units - it is requested to add a row at the bottom stating 2 units and mass for 2 units. | Ok. Will do. But the message was to baseline one unit and to address two units only when discussing the science cases.
| 5.4 | AJ | It is assumed that the payload unit will be provided with its own thermal control sub-system (radiators, MLI… sizing based on unit accommodation input provided by S/C), and that S/C TCS is only responsible for the survival heaters. Confirmation needed. | Confirmed. But the case of the sun-shield is under discussion whether it willl be included as part of the unit design or as a global S/C solution.
| 5.8.1. | BO | It is stated that no TM data will be generated in IDLE mode. The instrument shall deliver HK data in any mode (except it is switched off). In IDLE mode, a minimum rate of 2 commands per second are suggested. Furthermore, in case instrument is expected to receive commands, it will need to reply to these. | MEPS is unconfigured in IDLE mode, and will not generate any data. It accepts telecommands (TCs), so that it can be configured to another mode (e.g. Standby or Operational). This implies that to generate HK data after switch-on, MEPS has to be configured to transition to a new mode by TC from DPU. It is unclear to us what "a minimum rate of 2 commands per second" refers to in this context. MEPS will *not* directly reply to TCs (by e.g. ACK packets) in any mode. After having been configured to either Standby or Operational mode, MEPS will send HK packets regularly to DPU, which can be inspected to check the amount of TCs accepted by the sensor.
| 5.8.1 | CB | What is the difference between burst science data generation in nominal mode and burst mode? | None. Some additional packets might be generated, though we'd like MEPS to send "burst type" data to DPU all the time (bandwidth is plenty), and have the DPU decide what to do with them (based on its mode).
| 5.8.1 | SI | Several modes are described with overlapping functions. Please clarify and seperate the functions of "Calibration & Commissioning mode", "House Keeping Mode" and "Burst Mode". | Done in new ICD
| 5.8.1 | SI | Please provide a mode transition diagram, and a table with the functions of each mode, and proposed state transitions. | Done in new ICD
| 5.8.1 and 4.4 | SI | Please consolidate and clarify the relation between the "instrument software operation principle" modes and the modes discussed in 5.8.1. | N/A There is no software in MEPS. Just firmware.

## RM
Document | Section | Reviewer | Comment
| 1 | BO | Please clearly distinguish between requirements relevant for the S/C and relevant for the DPU.
MSSL-LGR-ICD-18005_ICD_RM_issue_A | 4.2. | BO | Shall the optional unit be considered in the baseline? What will be the difference in volume, mass and power consumption with respect to the full RM unit?
| 5.1. | BO | The instrument coordinate system in Fig 5-1 is not readable. Please provide an update
| 5.2.1. | BO | Please provide clarifications on RM unit locations, fields of view and line of sight, see also attached sketches. Please provide these informations also for the optional second unit (note that the "earth facing" side of the S/C is inclined by 30° to the L5-Earth line). A diagram clearly showing the fields of view shall be included in the next version of the ICD.
| 5.3.4. | BO | Please provide the unit volume allocation (height, length, width) in mm^3. (in case the optional unit varies, please also provide the information)
| 5.5. | BO | It is not possible to read Fig. 5-7 due to low resolution.
| 5.7.5., 6.3. | BO | The instrument shall provide the external radioactive source and take it back after finalizing the tests.
|  | BO | Are there any (survival) heaters envisaged in the design with a direct interface to the S/C?
| 5.2.1 | CB | At L5 the unit looking along the Parker spiral direction will have the Earth in the field of view. Considering this, is the second unit looking at Earth required?
| 5.2.1 | CB | Is the current location (corner of +Z and +X, S/C coordinate system) of RM acceptable from a thermal perspective?
| 5.3.4 | CB | This section should provide the envelope dimensions of the unit (main and optional). The purpose of the section is not to define the units used in the document (kg and mm).
| 5.3.6 | CB | This section refers to a picture but not picture is found. Please provide a picture showing the location of the connectors.
| 5.4 | AJ | It is understood that the thermal control sub-system of the RM is the responsibility of the payload team (sizing, procurement, installation), as RM is thermally decoupled from the s/c. Please confirm.
| 5.4.1 | CB | What is the purpose of specifying the "Optimum operating temperature range (℃): 0~30"? Should this be considered as a goal requirement, with the "Operation temperature range (min/max: ℃): -30/+45" as the threshold requirement?
| 5.5. | RL | Electrical interface diagram not readable in figure 5-7, please update.
| 5.5.1 | CB | The power budget needs to include 20% design maturity margin. It is not clear if this is included in the budget. Please update to to include the margin, or clearly show that it is included. Is the stated power consumption for 1 unit (looking along Parker spiral) or for 2 units (looking along Parker spiral and towards Earth)?
| 5.7 | CB | The spacecraft assembly facility will be ISO8 cleanroom with a local ISO5 area for instrument work before assembled to the spacecraft.
| 5.8.1 | SI | In "Nominal" mode "Central Computer" is understood to be/or running the "Preprocessing and Communication Unit". Is this correct ?
| 5.8.1 | SI | In "Diagnostic" mode the "Scientific-like Diagnostic Data (TBD) packages" would contain "raw" data for diagnostic purposes. Please describe the mode and what is produced.
| 5.8.3, 5.8.1 | SI | Please clarify how the periodic diagnostic and claibration runs are carried out using the modes discussed in 5.8.1.
| 5.8.3, 5.8.1 | SI | "Such procedures are automated in case of no failure behavior." Please describe in more detail how and where this is expected to be automated. DPU or Instrument level ?
| 5.8.3 | CB | How often are diagnostic runs required in flight, what is the duration of the diagnostic run each time it is performed, and does this need to be considered as an instrument unavailability?
| 5.9.2.3 | CB | What is the magnetic moment of the RM instrument? This is needed to assess its impact on other instruments.
| 6.2 | CB | What health and safety considerations need to be taken into account for performing the testing with the weak radioactive source? The instrument contractor shall manage the provision of the weak radioactive source to whichever site it is required and instrument contractor personnel shall conduct the necessary AIT tests.
| 6.2 | CB | It is not clear if long-term testing using cosmic muons is required or not, or how long it would take if it is required. Given that it requires an "extensive amount of time" it is very important to understand if it is required during System level AIT, and how long it would take to perform. We assume the test will take 2 hours until advised otherwise.

## XFM
Document | Section | Reviewer | Comment
MSSL-LGR-ICD-18006_ICD_XFM_issue_A | 4.3. | BO | We understand that the data packets are delivered to the DPU which then process and deliver them to the S/C.
| 5.2.1. | BO | If a thermal shield is required it shall be provided as part of the instrument design.
| 5.2.2. & 5.2.3 | BO | The "maximum mis-alignment from the sun of 1 degree" seems contradictory to the "pointing accuracy of the S/C is ±3°". We will take ±3° as the requirement until further clarified.
| 5.4.4. | BO | It is assumed that the S/C will provide power lines for the survival heaters.
| 5.7.1. | BO | Does the red tag item refer to the covers in front of the detector windows (or is it expected to have an additional shield with a red tag)?
| 5.3.2 | CB | The mass budget should clearly state what % design maturity margin is taken.
| 5.4.3 | AJ | The preferred option for s/c is to have a thermally isolated XFM. In this case it is understood that payload will be responsible for sizing/procurement/installation of the XFM thermal h/w, and s/c will provide the electrical lines for heaters, and the thermistors for the survival heaters.
| 5.4.4 | CB | For a thermally isolated instrument, the instrument radiator would need to be on the instrument +Z side (spacecraft +X side) to maximise the view of space. This would ensure the spacecraft body is not in the view, although the magnetometer boom may be in the view.
| 5.7.1 | CB | The spacecraft assembly facility will be ISO8 cleanroom with a local ISO5 area for instrument work before assembled to the spacecraft.
| 5.8.1 | SI | Please clarify the transition between the "Stand-by mode" and the "Operational mode" in both directions. Use two transition arrows for directions on the state diagram and do not mix dedicated transition commands with a transition which is automatic after all parameter commands are sent.
| 5.8.3 | CB | What is the duration of the annealing activities performed once every 3 months? Are any other activities required which will temporarily stop instrument operations (e.g. diagnostic activities)? Do these need to be considered as instrument unavailabilities?
| 5.9.2.3 | CB | What is the magnetic moment of the RM instrument? This is needed to assess its impact on other instruments.

## DPU
Document | Section | Reviewer | Comment
MSSL-LGR-ICD-18007_ICD_DPU_issue_A | 4.2.,5.5.1. | BO | It is understood that the S/C shall provide 2x(1N+1R) unregulated power interfaces.
| 4.2. | RL | IRD-DPU-FUN-001: The DPU provides on-board memory to store hours/days of instrument data – TBD volume – this could mean that for in-situ no platform mass memory allocation is needed – to be further iterated.
| 4.2. |  | IRD-DPU-SYS-006: please include redundant interfaces as well. It is understood that the spacecraft shall provide (1N+1R) SpW link
| 4.2. | BO | IRD-DPU-FUN-001: Is an additional memory / buffer needed on S/C side, or will all required memory for the in-situ instrument package be provided by the DPU?
| 4.3., 5.6.1. | BO | We understand that the nominal data rate is 10 kbps, and a high data rate is up to 100 kbps. When, how often and for which duration is the high data mode of 100 kbps delivered to the S/C? Is it expected to be downlinked directly, or stored on the S/C?
| 4.3. | BO | It is understood that there will be one box with the characteristics described in Table 4-3, providing the redundancy scheme as described throughout the document.
| 4.4. | SI | Please provide details of the SW description.
| 5.4 | AJ | Info still TBD. The payload TCS approach (coupled or decoupled from the s/c and responsabilities) needs to be clarified.
| 5.6.1 | CB | Burst mode: will the ground send a command to enter burst mode, or is it expected that the spacecraft will have an internal trigger to enter burst mode? If an internal trigger is expected, will this be in the DPU or is it expected to be in the platform which then sends a command to the DPU to enter burst mode? Same questions apply for exiting burst mode.
| General | CB | The individual instruments ICDs and DPU ICD do not provide any information about FDIR design. Do the instruments and/or DPU have the capability to monitor and detect failures? What action is taken in the event of a failure occuring?
| General | RL | Are there any discrete interfaces from the instruments? if yes, are they covered by the DPU and in which module?

## General I
Applicable | Comment
All | The ICDs are mainly top level descriptions which do not enable to evaluate the exact interface needs. It is not clear what is a requirement on the spacecraft and what is information only. Approach followed in PMI ICD with individual requirements with IDs is requested.
All | A burst mode seems to be foreseen for the instruments in case a solar event happens. This is in contradiction to the information provided at the System PM1, where it was communicated that the instruments will not change their usual measurements in case of a solar event
All | Is the burst mode equivalent to the high data rate presented in the DPU? Please clarify for how long and how often the high data rate will be expected. Is it expected that the data is directoly downlinked, or may it be stored on the S/C for a TBD duration?
All | The instruments (or instrument packages) are expected to be compatible with an unregulated bus voltage (26 - 34 V)provided by the spacecraft. This will be formulated in the spacecraft to instruments ICD.
All | Survival heaters seem not to be addressed in the ICDs. Please include.

## General All
Applicable | area | Comment
all instruments | admin | A distinction needs to be made for requirements which are applicable to the S/C and requirements which are applicable to the IPCU / DPU (for instruments)
IPCU /DPU | admin | A distinction needs to be made for requirements which are applicable to the S/C and requirements which are applicable to the instruments
All instruments , IPCU and DPU | admin | It should be common to all ICDs which electrical interfaces are described. An overview of interfaces function, amount, type and destination (IPCU/DPU or S/C) per instrument / DPU /IPCU should be provided.
All instruments , IPCU and DPU | admin | Please make detailed use of the change log and /or provide documents including "track changes" to facilitate the location of changes. Please also check for inconcsistencies between various documents provided (e.g., ICDs and budget report).
All instruments , IPCU and DPU | power | The power distribution concepts for 28V between remote and in-situ should be aligned. In-situ provides in the DPU the switching capability of power lines, potentially further capabilities as power conditioning etc. The IPCU relies on the S/C. Both concepts are considered feasible.
all instruments | power | Please provide nominal power, peak power, standby power including margins.
All instruments , IPCU and DPU | interface | Please include information on redundant interfaces (give the number of nominal and the number of redundant I/F).
All instruments | interface | Electrical interfaces (connectors) and purge interfaces shall be clearly defined. These should be close to the mechanical interface to the spacecraft mounting panel.
All instruments | thermal | If any instruments require a change of MLI at the launch site then two sets of MLI must be supplied by the instrument supplier.
All instruments | thermal | Details of thermal paint, radiator surfaces and MLI need to be provided to take into account in the design.
All instruments | thermal | For thermally isolated instruments the analysis of the instrument interface with the spacecraft is the instrument contractors responsibility and the provision of any thermally isolating washers/spacers is the responsibility of the instrument contractor.
All instruments, IPCU, DPU | mechanical | Please provide CAD models (step file) for all instruments and IPCU/DPU.
All instruments | cleanliness | Instrument providers shall provide cleanliness bagging compatible with purge, and seals/plugs which are compatible with purge and TVAC.
All instruments | cleanliness | End to end' release tests of doors/shutters when the instruments are on the spacecraft will be performed in an ISO 8 environment. If the instruments require specific protection in this environment then this must be designed in from the start.
All instruments | cleanliness | Spacecraft prime will not perform any operations in ISO 6 but will provide an ISO 6 environment for the instrument team to work in if required prior to installation on the spacecraft. The instrument, when closed, needs to be robust to an ISO 8 environment.
All instruments | cleanliness | No constraints on MOC and PAC levels. Please specify levels for external surfaces and apertures. The cleanliness level of internal surfaces can not be under responsibility of the S/C integrator (potential contamination before delivery to integrator).
All instruments | cleanliness | Please specify if purging will be required. An total (cummulative) interruption of 400 h TBC shall be acceptable for the instruments. Purging will not be planned during transports, launch campaign and shortly stopped during TVAC and mechanical tests. What is the acceptable purge outage in ISO 8 cleanroom environment and the required recovery time? The S/C integrator will provide purge flow with Gaseous Nitrogen GN2 class 5 TBC; spacecraft to instruments ICD will specify the gas and gas cleanliness to be used for purging as well as the maximum purge outage duration.
All instruments | cleanliness | Which instruments will be switched on during transfer phase?
All instruments , IPCU and DPU | FDIR | The FDIR approach for all instruments is undefined. It is very imortant to work with the instrument teams to define an acceptable FDIR approach keeping in mind the availability requirements for the whole System. Questions to be addressed are: How will fault be detected? Who will be responsible for monitoring and commanding instrument into a specific mode (e.g., IPCU/DPU or S/C), which mode transitions will be autonomously? Are there "recovery" times needed between different modes (e.g., safe mode to nominal mode, for example in case a certain thermal stability has to be reached)?
All instruments | FDIR | Please include the presence and purpose (measurement) of temperature sensors (for survival heaters) in the instrument ICD. This is asked to understand the FDIR concept.
All instruments | FDIR | Please include the presence and purpose (measurement) of other sensors in the instrument ICD. This is asked to understand the FDIR concept.
All instruments | FDIR | Which instruments will be switched on during transfer phase?