## Risks&Opportunities
critical
Comment | Title summarising the topic of the risk (e.g. PCDU, Launch, etc.) | This column indicates who is responsible for monitoring/performing the actions relevant to the specific risk . | This column indicates the status of the risk (i.e. draft, active, rejected, closed). See TAB "definitions" for status options and descriptions. WINDOW MENU | Brief description of what the risk is. Please use the appropriate language to formulate the risk description ("may", "could"). | This column defines what makes this a risk (e.g. the selected valve failed 80% of the time in XXX mission). Please refer only to ACTUAL facts. Please describe the context (assumptions) that leads to this risk. | This column aims at describing the effect of the occurrence of this risk would have on the Lagrange mission. "what I cannot achieve if this risk happens". | Impact/Severity associated with the specific risk. Please see the next TAB "Severity&Impact" for identifying the correct severity. Three difference columns: Performance, Schedule, Cost. These columns include a WINDOW MENU with various options amongst which to select. |  |  | Likelihood (probability of occurrence) of the specific risk. Please see TAB "Likelihood" for the definition of the likelihood categories. WINDOW MENU | Combined severity & likelihood risk. This aspect is important for the identification of what risk is considered acceptable at this stage of the project and which risk instead requires further investigation and/or implementation of specific mitigation plans. THIS COLUMN IS FILLED AUTOMATICALLY | This column shows the strategy to implement for the specific risk. | This column provides the plan of actions that will be put in place in the Phase AB1 to mitigate the severity/likelihood of this risk | This column provides the plan of actions that shall be put in place in the Phase B2CD to mitigate the severity/likelihood of this risk | This column indicates the final magnitude that is targeted via the implementation of the Phase AB1 & Phase B2CD plans. | This column shall state by when the actions relevant to this risk are due to be fully executed (e.g. Phase B1, by PDR, etc.)
Risk ID | Risk Title | Risk Owner | Status | Risk Description | Risk Context | Risk Effect | Performance | Schedule | Cost | Risk Likelihood | Current Risk Magnitude | Strategy | Plan AB1 | Plan B2CD | Target Magnitude | Due Date
LGR-R-1 | MEPS proton-ion low energy threshold | C. Martin | draft | MEPS 30keV lower energy limit may cannot be achieved. | The energy deposited in the first ion telescope detector may not be well determined due to the noise level | The particle identification in the low energy range will be more difficult to achieve. | 2 |  |  | B | B2 | MITIGATE | Tests, meetings with manufacturer | Tests, meetings with manufacturer | A2 | B2
LGR-R-2 | Funding | C. Martin | draft | Uncertain enough funding for phases B2-D | It is not clear whether the future funding will be enough to keep the key personnel and get the necessary resources during the life cycle. | Scope, schedule and quality will be affected by insufficient funding. | 2 | 3 |  | C | C3 | MITIGATE | Budget negotiations | Budget negotiations | A3 | B2
LGR-R-3 | Straylight | C. Martin | draft | Straylight may affect the MEPS detector performance | Reflected sunlight reaching the Si detectors will increase their noise | Detector affected by straylight can become unusable due to noise induced level. | 4 |  |  | B | B4 | MITIGATE | Modelizations, interaction with the PRIME and ESA | Modelizations, interaction with the PRIME and ESA | B2 | PDR
LGR-R-4 | Performance under solar illumination | C. Martin | draft | Solar Illumination may affect MEPS detector performance | Direct sunlight on the telescope collimator or on the detector themselves will increase the detector noise | Detector affected by direct sun illumination can become unusable due to noise induced level. | 4 |  |  | C | C4 | MITIGATE | Modelizations, interaction with the PRIME and ESA on accommodation | Modelizations, interaction with the PRIME and ESA on accommodation | B2 | PDR
LGR-R-5 | Schedule | C. Martin | draft | Schedule too tight | Schedule too tight for 4 major reviews and 4-5 models development in 4 years | FM delivery date may be affected |  | 3 |  | C | C3 | MITIGATE | Regular progress meetings | Regular progress meetings | B2 | PDR
LGR-R-6 | Thermal design | Ali Ravanbakhsh | draft | Challenging thermal design | The direct solar illumination in almost all accommodation studies could make the whole MEPS thermal design more challenging | Power allocation and instrument performance may be affected | 3 |  | 2 | A | A3 | MITIGATE | Modelizations, interaction with the PRIME and ESA | Modelizations, tests, interaction with the PRIME and ESA | A2 | PDR
LGR-R-7 | Structural design | Ali Ravanbakhsh | draft | Challenging structural design | The current S/C loads, instrument size and uneven mass distribution can make the whole MEPS structural design more challenging | Mechanical design and qualification could take longer and mass allocation may be affected. | 3 | 2 | 2 | A | A3 | MITIGATE | Modelizations, interaction with the PRIME and ESA | Modelizations, tests, interaction with the PRIME and ESA | A2 | PDR
LGR-R-8 | Space wire | C. Martin | draft | Not enough heritage | MEPS SpW is in untested prototype state. The implementation has been verified in simulation. | Development could take longer | 3 | 2 |  | A | A3 | MITIGATE | Normal work, continuous interaction with consortium and DPU | Normal work, continuous interaction with consortium and DPU, tests | A2 | PDR
LGR-R-9 | Accommodation | C. Martin | draft | Difficult accommodation of 4 double FoVs | 4 unobstructed double FoVs needs to be accommodated on the S/C | The obstruction of any FoV will lead to science loss | 3 |  |  | D | D3 | MITIGATE | Modelizations, interaction with the PRIME and ESA | Modelizations, interaction with the PRIME and ESA | B2 | PDR
LGR-R-10 | Uncertain human resources | C. Martin | draft | Difficulties to keep key personnel until funding is assured. | CAU is a projectized organization and the LGR funding does not allow to acquire new staff for A-B1 phases. It is not clear whether we can keep key personnel until the funding for next phases is assured | CAU may enter in the new LGR phases (B2-D) with lack of man power. |  | 3 |  | C | C3 | MITIGATE | Funding Negotiations | Funding Negotiations | A3 | End of 2019
LGR-R-11 | Central Part Procurement Agency | C. Martin | draft | EEE parts may not be procured through a CPPA | Procurement, qualification and part control is a huge task. In previous missions ESA subcontracted a CPPA to support the payload with these tasks | CAU will need an important increase of human resources to cope with a potential lack of CPPA support in this project. |  | 4 |  | C | C4 | MITIGATE | Negotiations with ESA | Negotiations with ESA | A3 | Starting B2
LGR-R-12 | [10 empty] | 0
LGR-R-13 | [10 empty] | 0
LGR-R-14 | [10 empty] | 0
LGR-R-15 | [10 empty] | 0
LGR-R-16 | [10 empty] | 0
LGR-R-17 | [10 empty] | 0
LGR-R-18 | [10 empty] | 0
LGR-R-19 | [10 empty] | 0
LGR-R-20 | [10 empty] | 0
Comment | Title summarising the topic of the opportunity (e.g. PCDU, Launch, etc.) | This column indicates who is responsible for monitoring/performing the actions relevant to the specific opportunity . | This column indicates the status of the opportunity (i.e. draft, active, rejected, closed). See TAB "definitions" for status options and descriptions. WINDOW MENU | Brief description of what the opportunity is. Please use the appropriate language to formulate the opportunity description ("may", "could"). | This column defines what makes this an opportunity. Please refer only to ACTUAL facts. Please describe the context (assumptions) that leads to this opportunity. | This column aims at describing the effect of the occurrence of this opportunity would have on the Lagrange mission. "what I can achieve if this opportunity happens". | Impact/Severity associated with the specific opportunity. Please see the next TAB "Severity&Impact" for identifying the correct severity. Three difference columns: Performance, Schedule, Cost. These columns include a WINDOW MENU with various options amongst which to select. |  |  | Likelihood (probability of occurrence) of the specific opportunity. Please see TAB "Likelihood" for the definition of the likelihood categories. WINDOW MENU | Combined severity & likelihood opportunity. This aspect is important for the identification of what opportunity should be pursued at this stage of the project and which one instead requires further investigation and/or implementation of specific plans. THIS COLUMN IS FILLED AUTOMATICALLY | This column shows the strategy to implement for the specific opportunity. | This column provides the plan of actions that will be put in place in the Phase AB1 to pursue this opportunity | This column provides the plan of actions that shall be put in place in the Phase B2CD to pursue this opportunity | This column indicates the final magnitude that is targeted via the implementation of the Phase AB1 & Phase B2CD plans. | This column shall state by when the actions relevant to this opportunity are due to be fully executed (e.g. Phase B1, by PDR, etc.)
Opportunity ID | Opportunity Title | Opportunity Owner | Status | Opportunity Description | Opportunity Context | Opportunity Effect | Performance | Schedule | Cost | Opportunity Likelihood | Current Opportunity Magnitude | Strategy | Plan AB1 | Plan B2CD | Target Magnitude | Due Date
LGR-O-1 | New detector developments | C. Martin | draft | Micron Semiconductors may develop a new series of detectors of better performance | Micron Semiconductors may develop a new series of detectors | Better detection threshold and particle determination | 2 |  |  | B | B2 | MITIGATE | Manufacturer Engagement | Manufacturer Engagement | C3 | Beginning of B2
LGR-O-2 | Projects extension | R. Wimmer | draft | Current projects may be extended | Some current projects may be extended and key LGR personnel may stay for at least one more year. | It would be possible to finish the LGR phase B1 with enough human resources | 2 | 2 |  | B | B2 | MITIGATE | Negotiation | N/A | C3 | End of 2019
LGR-O-3 | [10 empty] | 0
LGR-O-4 | [10 empty] | 0
LGR-O-5 | [10 empty] | 0
LGR-O-6 | [10 empty] | 0
LGR-O-7 | [10 empty] | 0
LGR-O-8 | [10 empty] | 0
LGR-O-9 | [10 empty] | 0
LGR-O-10 | [10 empty] | 0
LGR-O-11 | [10 empty] | 0
LGR-O-12 | [10 empty] | 0
LGR-O-13 | [10 empty] | 0
LGR-O-14 | [10 empty] | 0
LGR-O-15 | [10 empty] | 0
LGR-O-16 | [10 empty] | 0
LGR-O-17 | [10 empty] | 0
LGR-O-18 | [10 empty] | 0
LGR-O-19 | [10 empty] | 0
LGR-O-20 | [10 empty] | 0

## Severity&Impact
RISK Severity
Severity |  | Performance | Schedule | Cost
4 | Very High | Failure leading to the impossibility of fulfilling the instrument’s objectives | Delay resulting in instrument removed from the mission baseline | Cost increase resulting in instrument removal from baseline
3 | High | Failure resulting in a major performance reduction (30-50%) with respect to the observational measurements | Critical delay (3 to 6 months) with respect to the planned due date of the instrument | Critical increase in estimated cost by 500k - 1M€
2 | Medium | Failure resulting in a major performance reduction (10-30%) with respect to the observational measurements | Major delay (1 to 3 months) with respect to the planned due date of the instrument | Major increase in estimated cost by 100 - 500k€
1 | Low | Failure resulting in a substantial performance reduction (5-10%) with respect to the observational measurements | Significant delay (up to 1 month) with respect to the planned due date of the instrument | Significant increase in estimated cost by 100k€
Opportunity Impact
Impact |  | Performance | Schedule | Cost
4 | Very High | Instrument capable of achieving all objectives, improved performance of >50% | Provides an additional margin wrt to expected due date >6 months | Reduction in estimated cost by >1M€
3 | High | Instrument capable of achieving all objectives, improved performance of 30 - 50% | Provides an additional margin wrt to expected due date of 3-6 months | Reduction in estimated cost by 500k - 1M€
2 | Medium | Instrument capable of achieving all objectives, improved performance of 10 - 30% | Provides an additional margin wrt to expected due date of 1-3 months | Reduction in estimated cost by 100 - 500k€
1 | Low | Instrument capable of achieving all objectives, improved performance of 5 - 10% | Provides an additional margin wrt to expected due date of up to 1 month | Reduction in estimated cost by <100k€

## Likelihood
Score | Risk Likelihood | Definition | Score | Opportunity Likelihood | Definition
D | Nearly Certain | >75% | D | Nearly Certain | >75%
C | Likely | 50-75% | C | Likely | 50-75%
B | Possible | 25-50% | B | Possible | 25-50%
A | Unlikely | 1-25% | A | Unlikely | 1-25%

## Magnitude
RISK MAP
Likelihood | [5 empty] | Risk Index | Risk Magnitude | Proposed Actions
D | Low |  |  | LGR-R-9 |  | C4, D4 | Very High | Very high severity/criticality: R&O require immediate attention and response. Response plan shall be developed and actions to reduce or eliminate risks (or capture opportunities) implemented with high priority and management support.
C | Low |  |  | LGR-R-2, LGR-R-5, LGR-R-10 | LGR-R-4, LGR-R-11 | B3, B4, C3, D3 | High | High severity/criticality: R&O are significant with potential to become critical, they do not automatically require immediate management attention but close monitoring and follow-up of response actions shall be ensured at the appropriate level.
B | Very Low |  | LGR-R-1 |  | LGR-R-3 | A3, A4, B2, C2, D1, D2 | Medium | Medium severity/criticality: R&O may still have important consequences for the company, should be managed with response actions and monitored regularly.
A | Very Low |  |  | LGR-R-6, LGR-R-7, LGR-R-8 |  | A1, A2, B1, C1 | Low | Low severity/criticality: R&O being both unlikely to occur and not significant in their impact. They should be monitored and appropriate response actions should be taken to the extent deemed necessary unless subsequent assessment shows a substantial change.
1 | Very Low | Very Low | Very Low | Low | Low | C1, B1, A1, B2, A2, A3 | Very Low Risk | Acceptable Risk: see above.
| A | 1 | 2 | 3 | 4
Impact/Severity
OPPORTUNITY MAP
Likelihood | [5 empty] | Opportunity Index | Opportunity Magnitude | Proposed Actions
D | Low |  |  |  |  | C4, D4 | Very High | Very high severity/criticality: R&O require immediate attention and response. Response plan shall be developed and actions to reduce or eliminate risks (or capture opportunities) implemented with high priority and management support.
C | Very Low |  |  |  |  | B3, B4, C3, D3 | High | High severity/criticality: R&O are significant with potential to become critical, they do not automatically require immediate management attention but close monitoring and follow-up of response actions shall be ensured at the appropriate level.
B | Very Low |  |  | LGR-O-1, LGR-O-2 |  | A3, A4, B2, C2, D1, D2 | Medium | Medium severity/criticality: R&O may still have important consequences for the company, should be managed with response actions and monitored regularly.
A | Very Low |  |  |  |  | A1, A2, B1, C1 | Low | Low severity/criticality: R&O being both unlikely to occur and not significant in their impact. They should be monitored and appropriate response actions should be taken to the extent deemed necessary unless subsequent assessment shows a substantial change.
| A | 4 | 3 | 2 | 1
Impact/Severity

## definitions
Severity/impact | Likelihood | Status | Description
1 | A | ACTIVE | Accepted to be considered as a risk | A1 | A1
2 | B | DRAFT | Risk that is proposed | A2 | A2
3 | C | REJECTED | Risk not been accepted as a risk | A3 | A3
4 | D | CLOSED | No longer a risk | A4 | A4
|  |  |  | B1 | B1
|  |  |  | B2 | B2
|  | Strategy | Description | B3 | B3
|  | ACCEPT | only monitored, assessment of this risk/opporutnity should be done regularly at least monthly or after PMs/reviews | B4 | B4
|  | MITIGATE | reducing probability of the risk occurring or reducing the impact of its occurrence | C1 | C1
|  | AVOID | reducing the probability to zero (the risk will not occur) | C2 | C2
|  | TRANSFER | the consequence of the risk is transferred to another party (e.g. to the customer) | C3 | C3
|  |  |  | C4 | C4
|  |  |  | D1 | D1
|  |  |  | D2 | D2
|  |  |  | D3 | D3
|  |  |  | D4 | D4